## Risk Register
Risk ID | Asset / Process | Information | Threat / Event | Vulnerability | Existing Controls | L | I | Inherent Score | Level | Treatment | Risk Owner | Proposed Controls | Residual L | Residual I | Residual Score | Residual Level | Status
R-001 | Production Database | Customer data | Unauthorized access | Excessive privileges / credential compromise | MFA, RBAC | 4 | 5 | 20 | Critical | Mitigate | IT / Cloud Manager | Privileged access review; PAM; database monitoring | 2 | 5 | 10 | High | Open
R-002 | Employee Endpoints | Corporate/customer information | Phishing / malware | User susceptibility; outdated software | Endpoint protection, awareness | 4 | 4 | 16 | High | Mitigate | IT Manager | EDR tuning; patch SLA; phishing simulations | 2 | 4 | 8 | Moderate | Open
R-003 | Production Service | Service availability | Cloud/infrastructure failure | Insufficient redundancy | Cloud backups, monitoring | 3 | 5 | 15 | High | Mitigate | IT / Cloud Manager | Redundancy review; DR testing; capacity monitoring | 2 | 4 | 8 | Moderate | Open
R-004 | Source Code Repository | Source code | Unauthorized disclosure | Excessive repository permissions | Access control, code review | 3 | 5 | 15 | High | Mitigate | Development Manager | Quarterly access review; branch protection; secrets scanning | 2 | 4 | 8 | Moderate | Open
R-005 | Critical Suppliers | Customer/business data | Supplier compromise | Weak supplier assurance | Contracts, supplier review | 3 | 5 | 15 | High | Mitigate | Procurement Manager | Security due diligence; contractual clauses; periodic review | 2 | 4 | 8 | Moderate | Open
R-006 | Security Monitoring | Security logs | Failure to detect incident | Incomplete logging/alerting | Basic application logs | 4 | 4 | 16 | High | Mitigate | Security Officer | Centralized logging; alert rules; retention review | 2 | 4 | 8 | Moderate | Open
R-007 | Backup & Recovery | Business/Customer data | Backup failure | Untested recovery process | Scheduled backups | 3 | 4 | 12 | High | Mitigate | IT / Cloud Manager | Restore testing; backup monitoring; recovery objectives | 2 | 3 | 6 | Moderate | Open
R-008 | HR Information | Employee personal data | Unauthorized disclosure | Incorrect permissions | Access controls | 3 | 4 | 12 | High | Mitigate | HR Manager | Periodic access review; secure retention/disposal | 2 | 4 | 8 | Moderate | Open
R-009 | Production Systems | Operational data | Uncontrolled change | Inadequate change testing/approval | Change process | 3 | 4 | 12 | High | Mitigate | IT / Dev Manager | Formal approval; testing evidence; emergency review | 2 | 3 | 6 | Moderate | Open
R-010 | Cloud Administration | Credentials/configuration | Account compromise | Weak admin credential protection | MFA, restricted access | 3 | 5 | 15 | High | Mitigate | IT / Cloud Manager | PAM; admin session logging; break-glass controls | 1 | 5 | 5 | Moderate | Open

## Risk Summary
Level | Count | Action
Critical | 1 | Urgent treatment / senior management attention
High | 8 | Treatment and management oversight
Moderate | 1 | Monitor / additional treatment as appropriate
Low | 0 | Routine monitoring