## Risk Treatment Plan
Treatment ID | Risk ID | Risk Description | Current Level | Treatment Option | Treatment Action | Selected Control(s) | Control Owner | Risk Owner | Target Date | Expected Residual Risk | Priority | Status | Evidence / Completion Criteria
TP-001 | R-001 | Unauthorized access to customer database | Critical | Mitigate | Implement privileged access review, PAM and database monitoring | A.5.15 Access control; A.8.2 Privileged access rights; A.8.15 Logging | IT / Cloud Manager | IT / Cloud Manager | 2026-09-30 | Moderate / High | 1 | Planned | Access reviews; PAM configuration; monitoring evidence
TP-002 | R-002 | Phishing/malware affecting endpoints | High | Mitigate | Strengthen EDR, patch compliance and phishing awareness | A.6.3 Awareness; A.8.7 Malware protection; A.8.8 Technical vulnerabilities | IT Manager | IT Manager | 2026-09-30 | Moderate | 2 | Planned | EDR reports; patch dashboard; training records
TP-003 | R-003 | Production service outage | High | Mitigate | Review redundancy and perform disaster recovery testing | A.5.30 ICT readiness for business continuity; A.8.14 Redundancy | IT / Cloud Manager | Operations Manager | 2026-10-15 | Moderate | 3 | Planned | DR test report; architecture review
TP-004 | R-004 | Unauthorized source-code disclosure | High | Mitigate | Implement repository access review, branch protection and secrets scanning | A.5.15 Access control; A.8.4 Access to source code; A.8.28 Secure coding | Development Manager | Development Manager | 2026-09-30 | Moderate | 4 | Planned | Repository settings; access review; scan results
TP-005 | R-005 | Supplier compromise | High | Mitigate | Perform security due diligence and security clauses for critical suppliers | A.5.19 Supplier relationships; A.5.20 Supplier agreements; A.5.22 Monitoring supplier services | Procurement Manager | Procurement Manager | 2026-10-31 | Moderate | 5 | Planned | Supplier assessments; contracts; review records
TP-006 | R-006 | Insufficient security monitoring | High | Mitigate | Centralize security logs and implement alerting and retention requirements | A.8.15 Logging; A.8.16 Monitoring activities | Security Officer | Security Officer | 2026-10-15 | Moderate | 6 | Planned | Log inventory; alerts; retention settings
TP-007 | R-007 | Backup failure or weak recovery | High | Mitigate | Introduce scheduled restore tests and backup monitoring | A.8.13 Information backup; A.5.30 ICT readiness | IT / Cloud Manager | IT / Cloud Manager | 2026-09-30 | Moderate | 7 | Planned | Backup reports; restore test records
TP-008 | R-008 | Unauthorized disclosure of HR information | High | Mitigate | Review HR access and retention/disposal practices | A.5.15 Access control; A.8.10 Information deletion | HR Manager | HR Manager | 2026-10-31 | Moderate | 8 | Planned | Access review; disposal records
TP-009 | R-009 | Uncontrolled production change | High | Mitigate | Formalize change approval, testing and emergency-change review | A.8.32 Change management; A.8.31 Separation of development, test and production | IT / Dev Manager | IT Manager | 2026-09-30 | Moderate | 9 | Planned | Change tickets; approvals; test evidence
TP-010 | R-010 | Cloud administrator account compromise | High | Mitigate | Implement PAM, admin session logging and controlled emergency access | A.8.2 Privileged access rights; A.8.15 Logging; A.8.18 Privileged utility programs | IT / Cloud Manager | IT / Cloud Manager | 2026-09-30 | Moderate | 10 | Planned | PAM records; session logs; emergency access review

## Treatment Tracking
Treatment ID | Action Owner | Planned Action | Target Date | Completion % | Evidence Received | Residual Risk Reviewed? | Management Decision | Comments
TP-001 | IT / Cloud Manager | Implement privileged access review, PAM and database monitoring | 2026-09-30 | 0% | No | No | Pending
TP-002 | IT Manager | Strengthen EDR, patch compliance and phishing awareness | 2026-09-30 | 0% | No | No | Pending
TP-003 | IT / Cloud Manager | Review redundancy and perform disaster recovery testing | 2026-10-15 | 0% | No | No | Pending
TP-004 | Development Manager | Implement repository access review, branch protection and secrets scanning | 2026-09-30 | 0% | No | No | Pending
TP-005 | Procurement Manager | Perform security due diligence and security clauses for critical suppliers | 2026-10-31 | 0% | No | No | Pending
TP-006 | Security Officer | Centralize security logs and implement alerting and retention requirements | 2026-10-15 | 0% | No | No | Pending
TP-007 | IT / Cloud Manager | Introduce scheduled restore tests and backup monitoring | 2026-09-30 | 0% | No | No | Pending
TP-008 | HR Manager | Review HR access and retention/disposal practices | 2026-10-31 | 0% | No | No | Pending
TP-009 | IT / Dev Manager | Formalize change approval, testing and emergency-change review | 2026-09-30 | 0% | No | No | Pending
TP-010 | IT / Cloud Manager | Implement PAM, admin session logging and controlled emergency access | 2026-09-30 | 0% | No | No | Pending