## Actions
Action ID | Source | Decision / Action | Reason | Owner | Priority | Due Date | Status | Effectiveness Check
MRA-001 | KRI Review | Escalate critical vulnerability remediation | KRI above target | Security Manager | High | 2026-08-20 | Open | Verify closure and SLA performance
MRA-002 | Audit Finding | Implement document review reminders | Reduce overdue review risk | ISMS Manager | Medium | 2026-09-01 | Open | Check next review cycle
MRA-003 | Resource Review | Add role-based security training | Improve competence | HR/Security | Medium | 2026-10-01 | Open | Review assessment results