## Improvement Register
Improvement ID | Source | Improvement Opportunity | Current State | Desired State | Priority | Owner | Action | Target Date | Status | Effectiveness Measure
IMP-001 | Internal Audit | Strengthen document review monitoring | Manual tracking | Central review calendar with escalation | Medium | ISMS Manager | Implement review reminder and escalation process | 2026-09-01 | Open | No overdue controlled documents
IMP-002 | KPI/KRI | Improve critical vulnerability remediation | One critical item exceeded desired performance | Critical vulnerabilities escalated within defined SLA | High | Security Manager | Weekly critical vulnerability review | 2026-08-20 | Open | >=95% within SLA
IMP-003 | Management Review | Expand role-based security training | General awareness training | Role-specific modules for admins/developers | Medium | HR/Security | Develop role-based training modules | 2026-10-01 | Open | Assessment scores and completion
IMP-004 | Operational Evidence | Improve evidence traceability | Evidence stored across registers | Central evidence index | Medium | ISMS Manager | Maintain master evidence index | 2026-09-15 | In Progress | Sample evidence traceable to control