## Control Improvements
Control | Current Maturity | Issue / Gap | Improvement Action | Owner | Priority | Target | Status | Evidence
A.5.18 Access Rights | Implemented | Review reminders manual | Automate review reminders | IT Manager | Medium | Q4 2026 | Open | Access Review Record
A.8.8 Vulnerability Management | Implemented with improvement | Critical remediation escalation needs strengthening | Weekly critical vulnerability review | Security Manager | High | Aug 2026 | In Progress | Vulnerability Register
A.8.15 Logging | Implemented | Alert tuning opportunity | Tune high-value detection rules | Security Manager | High | Sep 2026 | Open | Monitoring Review
A.6.3 Awareness | Implemented | Role-based content limited | Add administrator/developer modules | HR/Security | Medium | Oct 2026 | Open | Training Records