## Assessment
Action ID | Gap | Action | Owner | Target | Priority | Status
A-01 | G-01 | Formalize privacy governance charter | Privacy Lead | Q4 2026 | High | Open
A-02 | G-02 | Implement DSAR case-management workflow | Privacy Lead | Q4 2026 | High | Open
A-03 | G-03 | Complete transfer assessments | Privacy/Procurement | Q4 2026 | High | Open
A-04 | G-04 | Implement retention review and deletion evidence | IT/Data Owners | Q1 2027 | Medium | Open
A-05 | G-05 | Standardize processor reviews | Procurement | Q1 2027 | Medium | Open