## Risk Register
ABC Cloud Technologies Ltd. — Information Security Risk Register
Portfolio Project ¦ Fictional Organization ¦ Qualitative 5×5 risk methodology ¦ Version 1.0 ¦ August 2026
Risk ID | Asset ID | Asset / Process | Risk Scenario | Threat | Vulnerability / Weakness | Existing Control | Control Effectiveness | Likelihood (1-5) | Impact (1-5) | Inherent Risk Score | Inherent Risk Rating | Risk Owner | Treatment Decision | Treatment Action | Residual Likelihood (1-5) | Residual Impact (1-5) | Residual Risk Score | Residual Risk Rating | Target Date | Status | Evidence / Reference
R-001 | A-001 | Customer Information Database | Unauthorized access to customer information could result in data disclosure, regulatory exposure, and reputational damage. | External attacker / compromised account | Excessive privileges or compromised user credentials | Role-based access; MFA (simulated); database access restrictions | Partially Effective | 4 | 5 | 20 | Critical | Head of Customer Operations | Mitigate | Perform quarterly access reviews, enforce MFA for all privileged access, and strengthen database monitoring. | 3 | 5 | 15 | High | 2026-09-30 | Open | Access review; IAM configuration; database logs
R-002 | A-003 | Source Code Repository | Unauthorized access or malicious modification of source code could introduce vulnerabilities or expose intellectual property. | Compromised developer account / malicious insider | Weak repository permissions or inadequate branch protection | Repository permissions; MFA; branch protection (simulated) | Partially Effective | 3 | 5 | 15 | High | Engineering Lead | Mitigate | Enforce MFA, least privilege, protected branches, mandatory peer review, and periodic repository access review. | 2 | 5 | 10 | High | 2026-09-30 | Open | GitHub settings; access review; pull-request evidence
R-003 | A-004 | AWS Production Environment | Misconfiguration of cloud resources could expose systems or sensitive data and cause service disruption. | Cloud misconfiguration / external attacker | Configuration drift, excessive permissions, or publicly exposed resources | IAM; logging; security monitoring; backups (simulated) | Partially Effective | 4 | 5 | 20 | Critical | IT Manager | Mitigate | Implement secure configuration baselines, continuous configuration monitoring, least privilege, and periodic cloud security reviews. | 2 | 5 | 10 | High | 2026-10-15 | Open | AWS configuration baseline; IAM review; monitoring reports
R-004 | A-005 | SaaS Production Application | Application vulnerability could be exploited to compromise customer accounts or application data. | External attacker | Insufficient secure development/testing controls | Secure deployment process; monitoring (simulated) | Partially Effective | 4 | 5 | 20 | Critical | Engineering Lead | Mitigate | Strengthen SDLC security testing, vulnerability scanning, code review, and remediation tracking. | 2 | 5 | 10 | High | 2026-10-31 | Open | SDLC procedure; scan reports; remediation tickets
R-005 | A-009 | Identity and Access Management | Compromised credentials could provide unauthorized access to multiple critical systems. | Phishing / credential theft | Inconsistent MFA coverage and excessive access privileges | Password policy; MFA for selected accounts; access reviews (simulated) | Partially Effective | 4 | 5 | 20 | Critical | IT Manager | Mitigate | Implement MFA for all users, privileged access controls, joiner-mover-leaver procedures, and quarterly access reviews. | 2 | 5 | 10 | High | 2026-09-15 | Open | MFA report; access review; JML records
R-006 | A-008 | Employee Laptops | Loss, theft, or malware infection of an endpoint could expose corporate or customer information. | Device theft / malware | Remote endpoints may be exposed outside controlled premises | Endpoint protection; encryption; device management (simulated) | Partially Effective | 3 | 4 | 12 | High | IT Manager | Mitigate | Verify full-disk encryption, endpoint compliance, patching, remote wipe, and centralized endpoint monitoring. | 2 | 4 | 8 | Medium | 2026-09-30 | Open | Endpoint compliance report; encryption status; patch report
R-007 | A-011 | Backup Repository | Backup failure or ransomware could prevent recovery of critical systems and information. | Ransomware / backup failure | Insufficient backup isolation, testing, or recovery validation | Scheduled backups; encryption; restricted access (simulated) | Partially Effective | 3 | 5 | 15 | High | IT Manager | Mitigate | Implement immutable/offline backup protection and perform documented restore tests at defined intervals. | 2 | 5 | 10 | High | 2026-10-15 | Open | Backup logs; restore test report
R-008 | A-010 | Security Logs and Monitoring | Insufficient monitoring could delay detection and response to a security incident. | Attacker activity / insider threat | Incomplete log collection, alerting, or retention | Centralized logging and alerting (simulated) | Partially Effective | 3 | 4 | 12 | High | Security Lead | Mitigate | Define logging requirements, monitor critical events, tune alerts, and establish log retention and review procedures. | 2 | 4 | 8 | Medium | 2026-10-15 | Open | SIEM/logging configuration; alert review records
R-009 | A-016 | VPN / Remote Access Service | Unauthorized remote access could allow attackers to reach internal or sensitive resources. | Credential compromise / brute force | Weak authentication or excessive remote access permissions | Authentication; encrypted connectivity; access restrictions (simulated) | Partially Effective | 3 | 4 | 12 | High | IT Manager | Mitigate | Enforce MFA, restrict remote access by role, review VPN logs, and remove inactive accounts. | 2 | 4 | 8 | Medium | 2026-09-30 | Open | VPN configuration; access list; logs
R-010 | A-020 | CI/CD Pipeline | Compromise of the deployment pipeline could allow malicious code or unauthorized changes to reach production. | Supply-chain attacker / compromised developer | Excessive pipeline permissions or weak deployment approvals | Protected branches; deployment approvals (simulated) | Partially Effective | 3 | 5 | 15 | High | Engineering Lead | Mitigate | Separate development and production privileges, protect secrets, require approval for production deployments, and audit pipeline activity. | 2 | 5 | 10 | High | 2026-10-31 | Open | Pipeline configuration; deployment approvals; secret-management evidence
R-011 | A-006 | Microsoft 365 Tenant | Phishing or account compromise could expose corporate email and documents. | Phishing / credential theft | User susceptibility and incomplete MFA coverage | MFA for selected users; access controls; audit logs (simulated) | Partially Effective | 4 | 4 | 16 | High | IT Manager | Mitigate | Deploy organization-wide MFA, phishing awareness exercises, conditional access, and periodic sign-in monitoring. | 2 | 4 | 8 | Medium | 2026-09-15 | Open | MFA report; conditional access; training records
R-012 | A-017 | Customer Contracts | Unauthorized disclosure or alteration of contracts could create legal, commercial, or reputational consequences. | Unauthorized access / insider threat | Inappropriate document permissions or weak version control | Access restrictions; document permissions; backups (simulated) | Partially Effective | 3 | 4 | 12 | High | Legal & Compliance Manager | Mitigate | Implement restricted contract repositories, role-based permissions, version control, and periodic access review. | 2 | 4 | 8 | Medium | 2026-10-15 | Open | Repository permissions; access review; version history

## Risk Methodology
Item | Method
Likelihood | 1 Rare; 2 Unlikely; 3 Possible; 4 Likely; 5 Almost Certain
Impact | 1 Insignificant; 2 Minor; 3 Moderate; 4 Major; 5 Severe
Risk Score | Likelihood × Impact
1–4 | Low
5–9 | Medium
10–16 | High
17–25 | Critical
Treatment — Mitigate | Reduce likelihood and/or impact by implementing or improving controls.
Treatment — Avoid | Stop or change the activity causing the risk.
Treatment — Transfer | Share the risk with another party, such as through insurance or contractual arrangements.
Treatment — Accept | Formally accept the risk within defined management risk tolerance.
Residual Risk | Risk remaining after existing and planned controls are considered.
Important | Scores in this portfolio are simulated and should be validated with business owners in a real assessment.