## Risk Treatment Plan
ABC Cloud Technologies Ltd. — Risk Treatment Plan
Portfolio Project ¦ Treatment actions derived from Risk Register ¦ Version 1.0 ¦ August 2026
Treatment ID | Risk ID | Asset ID | Risk Description | Current Residual Risk | Treatment Decision | Treatment Action | Control / Measure to Implement | Risk Owner | Action Owner | Priority | Target Date | Status | Expected Residual Likelihood | Expected Residual Impact | Expected Residual Score | Expected Residual Rating | Evidence / Completion Criteria
T-001 | R-001 | A-001 | Unauthorized access to customer information | High | Mitigate | Perform quarterly access reviews and strengthen privileged database access. | Enforce MFA for privileged access; least-privilege roles; quarterly access certification; database activity monitoring. | Head of Customer Operations | IT & Security | Critical | 2026-09-30 | Open | 2 | 5 | 10 | High | Approved access review; MFA evidence; database monitoring configuration; signed access certification.
T-002 | R-002 | A-003 | Unauthorized access or malicious modification of source code | Medium | Mitigate | Strengthen GitHub repository protection and developer access governance. | Mandatory MFA; least privilege; protected branches; mandatory peer review; quarterly repository access review. | Engineering Lead | Engineering & Development | High | 2026-09-30 | Open | 2 | 5 | 10 | High | GitHub settings export; access review; protected branch evidence; sample approved pull requests.
T-003 | R-003 | A-004 | AWS cloud misconfiguration could expose systems or data | Medium | Mitigate | Implement secure cloud configuration baselines and continuous review. | AWS security baseline; least privilege IAM; configuration monitoring; periodic cloud security assessment. | IT Manager | IT & Security | Critical | 2026-10-15 | Open | 2 | 5 | 10 | High | Approved baseline; configuration assessment; IAM review; remediation records.
T-004 | R-004 | A-005 | Application vulnerability could compromise customer accounts/data | Medium | Mitigate | Strengthen secure software development and vulnerability management. | SAST/DAST or equivalent testing; dependency scanning; secure code review; remediation SLA; security testing before production. | Engineering Lead | Engineering & Development | Critical | 2026-10-31 | Open | 2 | 5 | 10 | High | SDLC procedure; scan reports; code-review evidence; vulnerability remediation tickets.
T-005 | R-005 | A-009 | Compromised credentials could provide broad unauthorized access | Medium | Mitigate | Implement organization-wide MFA and formal joiner-mover-leaver controls. | MFA for all users; privileged access controls; quarterly access reviews; documented account lifecycle process. | IT Manager | IT & Security | Critical | 2026-09-15 | Open | 2 | 5 | 10 | High | MFA coverage report; JML procedure; access review records; terminated-account evidence.
T-006 | R-006 | A-008 | Lost, stolen, or infected endpoint could expose information | Medium | Mitigate | Improve endpoint security and device compliance monitoring. | Full-disk encryption; EDR/endpoint protection; patch compliance; remote wipe; centralized device management. | IT Manager | IT & Security | High | 2026-09-30 | Open | 2 | 4 | 8 | Medium | Endpoint compliance dashboard; encryption report; patch report; remote-wipe test.
T-007 | R-007 | A-011 | Backup failure or ransomware could prevent recovery | Medium | Mitigate | Protect backups against ransomware and validate recovery capability. | Immutable/offline backup copy; restricted backup administration; scheduled restore tests; documented recovery objectives. | IT Manager | IT & Security | Critical | 2026-10-15 | Open | 2 | 5 | 10 | High | Backup configuration; immutable-copy evidence; restore-test report; recovery test record.
T-008 | R-008 | A-010 | Insufficient monitoring could delay incident detection | Medium | Mitigate | Formalize centralized logging, alerting, review, and retention requirements. | Critical-event logging; centralized monitoring; alert tuning; log retention standard; periodic review. | Security Lead | IT & Security | High | 2026-10-15 | Open | 2 | 4 | 8 | Medium | Logging standard; SIEM/logging configuration; alert tickets; periodic log-review record.
T-009 | R-009 | A-016 | Unauthorized remote access could reach sensitive resources | Medium | Mitigate | Strengthen remote access authentication and authorization. | MFA; role-based VPN access; inactive-account removal; periodic VPN log review; restricted administrative access. | IT Manager | IT & Security | High | 2026-09-30 | Open | 2 | 4 | 8 | Medium | VPN configuration; access list; MFA report; log-review evidence.
T-010 | R-010 | A-020 | CI/CD compromise could introduce malicious changes into production | Medium | Mitigate | Separate development and production privileges and strengthen deployment approvals. | Protected production branch; deployment approval; secrets management; least-privilege service accounts; pipeline audit logs. | Engineering Lead | Engineering & Development | Critical | 2026-10-31 | Open | 2 | 5 | 10 | High | Pipeline configuration; deployment approval records; secrets-management evidence; audit logs.
T-011 | R-011 | A-006 | Phishing or account compromise could expose Microsoft 365 data | Medium | Mitigate | Deploy full MFA and phishing-resistant identity controls for sensitive accounts. | Organization-wide MFA; conditional access; phishing awareness; suspicious sign-in monitoring. | IT Manager | IT & Security | Critical | 2026-09-15 | Open | 2 | 4 | 8 | Medium | MFA coverage; conditional-access policies; training records; sign-in monitoring evidence.
T-012 | R-012 | A-017 | Unauthorized disclosure or alteration of customer contracts | Medium | Mitigate | Restrict contract repositories and strengthen document governance. | Role-based permissions; version control; periodic access review; retention rules; restricted sharing. | Legal & Compliance Manager | Legal & Compliance | High | 2026-10-15 | Open | 2 | 4 | 8 | Medium | Repository permissions; access review; version history; retention configuration.

## Treatment Summary
Treatment Plan Summary
Total treatment actions | 12
Mitigate | 12
Avoid | 0
Transfer | 0
Accept | 0
Critical priority actions | 7
High priority actions | 5
Open actions | 12
Target period | 15 September 2026 – 31 October 2026

## Treatment Methodology
Treatment Planning Guidance
Mitigate | Implement or improve controls to reduce likelihood and/or impact.
Avoid | Stop, discontinue, or redesign the activity creating the risk.
Transfer | Share financial or operational consequences with another party, where appropriate.
Accept | Formally accept the remaining risk within approved risk tolerance.
Priority | Critical = urgent management attention; High = priority treatment; Medium/Low = planned or routine treatment.
Expected Residual Risk | The risk level expected after the treatment action is implemented and operating effectively.
Completion Criteria | Objective evidence that can demonstrate the treatment action was implemented.
Portfolio Note | All treatment actions, owners, dates, and expected risk scores are simulated for this portfolio project.