## Corrective Action Register
ABC Cloud Technologies Ltd. — Corrective Action Register
Portfolio Project ¦ Corrective actions derived from simulated audit findings ¦ Version 1.0 ¦ August 2026
CAR ID | Evidence ID | Control Ref | Finding Type | Finding Statement | Correction / Immediate Action | Root Cause | Corrective Action | Responsible Owner | Priority | Target Date | Status | Implementation Evidence | Effectiveness Check | Effectiveness Result | Closure Date | Verifier | Notes
CAR-001 | E-002 | A.5.17 | Observation | MFA coverage is incomplete for some accounts, creating avoidable authentication risk. | Review current MFA coverage and identify accounts without MFA. | Authentication requirements have not been applied consistently across all account types. | Implement organization-wide MFA and define exceptions with documented risk approval. | IT Manager | Critical | 2026-09-15 | Open | MFA coverage report showing 100% applicable coverage; approved exception register where required. | Sample user and privileged accounts after implementation; verify MFA enforcement and exception approvals. | Pending |  | Security Lead
CAR-002 | E-003 | A.8.4 | Observation | Periodic source-code repository access-review evidence is not consistently retained. | Perform a current repository access review and remove unnecessary permissions. | Access-review responsibility and evidence-retention requirements are not formally embedded in the repository governance process. | Establish quarterly repository access certification with documented owner approval and retained evidence. | Engineering Lead | High | 2026-09-30 | Open | Quarterly access review report; approval records; removed-account evidence. | Sample repositories and compare current access against approved access lists. | Pending |  | Security Lead
CAR-003 | E-004 | A.8.9 | Minor Nonconformity | Continuous configuration monitoring and documented exception handling are incomplete. | Document known configuration exceptions and assess current cloud configurations. | Configuration management is treated as a baseline activity rather than a continuously monitored control. | Implement continuous configuration monitoring, defined secure baselines, alerting, exception approval, and remediation tracking. | IT Manager | Critical | 2026-10-15 | Open | Configuration baseline; monitoring dashboard; alerts; exception register; remediation tickets. | Review sampled cloud resources for compliance and verify exceptions have valid approval and remediation dates. | Pending |  | Security Lead
CAR-004 | E-006 | A.8.13 | Major Nonconformity | Documented restore testing is not consistently performed or retained. | Confirm current backup jobs and perform an immediate restore test for a critical workload. | Backup management focuses on successful backup execution without sufficient validation of recoverability. | Define and execute a formal restore-testing schedule aligned to business recovery requirements, with documented results and corrective actions. | IT Manager | Critical | 2026-10-15 | Open | Approved restore-test schedule; successful restore report; test evidence; corrective-action records. | Independently review a completed restore test and confirm recovery objectives were achieved. | Pending |  | Security Lead
CAR-005 | E-007 | A.8.15 | Observation | Evidence of periodic log review is not consistently retained. | Perform a current review of critical security logs and record the review. | Log-review responsibility and evidence-retention requirements are not sufficiently formalized. | Define log-review frequency, responsible roles, required review evidence, and escalation criteria. | Security Lead | High | 2026-10-15 | Open | Log-review procedure; completed review records; escalation tickets where applicable. | Sample subsequent review periods and verify reviews were completed on schedule. | Pending |  | Security Manager
CAR-006 | E-008 | A.8.16 | Minor Nonconformity | Alert tuning and documented monitoring review evidence are incomplete. | Review existing alerts and prioritize critical monitoring use cases. | Monitoring has grown reactively without a formally approved use-case catalogue and review cadence. | Establish monitoring use cases, alert severity criteria, tuning reviews, escalation procedures, and periodic reporting. | Security Lead | High | 2026-10-15 | Open | Monitoring use-case catalogue; alert rules; tuning records; escalation records; monthly monitoring report. | Sample alerts and verify they are appropriately classified, investigated, and escalated. | Pending |  | Security Manager
CAR-007 | E-011 | A.6.3 | Minor Nonconformity | Security awareness completion and phishing-simulation evidence are incomplete. | Identify personnel without current security awareness training. | Awareness activities are not tracked through a complete, risk-based annual program. | Implement an annual security awareness plan, completion tracking, phishing simulations, and management reporting. | IT Manager | High | 2026-09-30 | Open | Training plan; completion dashboard; phishing simulation results; awareness materials. | Sample personnel records and verify completion; review phishing metrics for improvement. | Pending |  | HR / Security
CAR-008 | E-013 | A.8.28 | Minor Nonconformity | Consistent evidence of security testing before production release is incomplete. | Review recent releases and identify whether security testing was performed. | Security testing is not consistently enforced as a documented release gate. | Integrate applicable security testing into the SDLC and require documented security sign-off for defined release types. | Engineering Lead | Critical | 2026-10-31 | Open | SDLC procedure; pipeline gate; scan results; security sign-off; remediation tickets. | Sample subsequent production releases and verify required security testing was completed before deployment. | Pending |  | Security Lead
CAR-009 | E-014 | A.8.31 | Observation | Periodic review of environment and deployment privileges should be better documented. | Review current development, test, and production privileges. | Privilege review is performed operationally but not consistently documented as a formal recurring activity. | Add quarterly environment privilege certification to access governance procedures. | Engineering Lead | High | 2026-10-31 | Open | Privilege review report; approvals; removed-access records. | Review the next certification cycle and verify unauthorized privileges are identified and removed. | Pending |  | Security Lead
CAR-010 | E-015 | A.8.2 | Major Nonconformity | Formal quarterly privileged-access certification is incomplete for critical systems. | Identify privileged accounts and immediately validate current business need and approval. | Privileged-access governance lacks a consistent organization-wide review cadence and evidence requirement. | Establish quarterly privileged-access certification, separate administrative accounts where appropriate, and retain approvals and review results. | IT Manager | Critical | 2026-09-30 | Open | Privileged-access register; quarterly certification; approval records; admin logs. | Sample critical systems and verify all privileged accounts have current approval and appropriate access. | Pending |  | Security Manager

## CAR Summary
Corrective Action Summary
Total corrective actions | 10
Major Nonconformities | 2
Minor Nonconformities | 4
Observations | 4
Critical priority actions | 5
High priority actions | 5
Open actions | 10
Effectiveness checks pending | 10
Corrective Action Lifecycle
1. Correction | Address the immediate issue or containment need.
2. Root Cause | Determine why the nonconformity or gap occurred.
3. Corrective Action | Implement changes to prevent recurrence.
4. Evidence | Collect objective evidence that the action was implemented.
5. Effectiveness Check | Verify the action actually prevents recurrence or improves control performance.
6. Closure | Independent/authorized verifier confirms completion and effectiveness.

## CAR Guidance
Corrective Action Guidance
Correction | The immediate action taken to address the detected issue. It does not necessarily prevent recurrence.
Root Cause | The underlying reason the problem occurred. Root-cause analysis should avoid simply restating the finding.
Corrective Action | The systemic action intended to prevent recurrence.
Evidence | Objective evidence should demonstrate implementation, not just a statement that the action was completed.
Effectiveness Check | Verification should test whether the control now works as intended over an appropriate period or sample.
Closure | Closure should be approved only after implementation and effectiveness requirements are satisfied.
Portfolio Note | All findings, root causes, actions, dates, and verification results are simulated for portfolio purposes.