## Internal Audit Plan
ABC Cloud Technologies Ltd. — ISO/IEC 27001 Internal Audit Plan
Portfolio Project ¦ Simulated internal audit programme ¦ ISO/IEC 27001:2022 ¦ Version 1.0 ¦ August 2026
Audit ID | IA-2026-001 | Audit Type | Internal ISMS Audit | Planned Period | August 24–28, 2026 | Lead Auditor | GRC / Compliance Lead
ISMS Scope | ABC Cloud Technologies Ltd. — customer information, applications, cloud infrastructure, source code, identity, endpoints, backups and supporting processes | Audit Criteria | ISO/IEC 27001:2022; approved ISMS policies; Statement of Applicability; risk treatment plan; applicable legal/contractual requirements | Audit Objective | Assess conformity, implementation and operating effectiveness of selected ISMS processes and controls | Status | Planned
Audit Schedule and Activities
Activity ID | Date | Time | Process / Area | Audit Objective | Audit Criteria / Control References | Auditee / Owner | Auditor | Method | Evidence Expected | Status | Notes | Opening / Closing | Risk Focus
IA-01 | 2026-08-24 | 09:30–10:00 | Opening Meeting | Confirm scope, objectives, criteria, methods and logistics. | ISO/IEC 27001 audit planning; ISMS scope | Executive Sponsor / Process Owners | Lead Auditor | Interview / meeting | Attendance; scope confirmation; agenda | Planned |  | Opening | All high risks
IA-02 | 2026-08-24 | 10:00–12:00 | ISMS Governance & Risk Management | Assess governance, risk assessment, treatment, objectives and management oversight. | Clauses 4–10; Risk Register; Risk Treatment Plan | GRC / Compliance Lead | Lead Auditor | Interview; document review | Risk methodology; risk register; treatment plan; management review records | Planned |  | Audit Activity | Enterprise risk
IA-03 | 2026-08-24 | 13:00–15:00 | Statement of Applicability | Verify control applicability decisions are justified and traceable to risks and requirements. | SoA; Risk Assessment; Annex A controls | GRC / Compliance Lead | Lead Auditor | Document review; sampling | Approved SoA; control justifications; evidence references | Planned |  | Audit Activity | Control coverage
IA-04 | 2026-08-25 | 09:30–12:00 | Access & Identity Management | Verify access is authorized, least-privilege, reviewed and removed when no longer required. | A.5.15, A.5.16, A.5.17, A.8.2 | IT Manager / Security Lead | Lead Auditor | Interview; sampling; evidence review | Access matrix; MFA report; privileged-access register; access reviews | Planned |  | Audit Activity | Unauthorized / privileged access
IA-05 | 2026-08-25 | 13:00–15:00 | Cloud & Configuration Management | Assess secure configuration baselines, monitoring and exception management. | A.5.23, A.8.9 | IT Manager | Technical Auditor | Configuration review; sampling | Cloud baseline; configuration reports; exception register | Planned |  | Audit Activity | Cloud misconfiguration
IA-06 | 2026-08-26 | 09:30–11:30 | Vulnerability & Endpoint Security | Assess vulnerability identification, prioritization, remediation and malware protection. | A.8.7, A.8.8 | IT / Engineering Lead | Technical Auditor | Evidence review; sampling | Vulnerability scans; remediation tickets; endpoint status | Planned |  | Audit Activity | Exploitation / malware
IA-07 | 2026-08-26 | 13:00–15:00 | Backup & Business Continuity | Verify backup protection, retention, recovery objectives and restore testing. | A.8.13, A.5.30 | IT Manager | Lead Auditor | Interview; evidence review; sample test records | Backup logs; restore tests; RTO/RPO; recovery plan | Planned |  | Audit Activity | Data loss / service disruption
IA-08 | 2026-08-27 | 09:30–12:00 | Logging, Monitoring & Incident Management | Assess logging, monitoring, alert review, incident response and escalation. | A.8.15, A.8.16, A.5.24, A.5.26 | Security Lead | Technical Auditor | Evidence review; interviews; sampling | SIEM records; alert tickets; incident records; escalation evidence | Planned |  | Audit Activity | Detection / response
IA-09 | 2026-08-27 | 13:00–15:30 | Secure Development & Change Management | Assess secure coding, source-code access, environment separation and production change controls. | A.8.4, A.8.28, A.8.31, A.8.32 | Engineering Lead | Technical Auditor | Walkthrough; sampling; evidence review | Repository permissions; code review; security testing; change tickets | Planned |  | Audit Activity | Application compromise / unauthorized change
IA-10 | 2026-08-28 | 09:30–11:00 | People & Remote Working | Assess security awareness, training and controls for remote working. | A.6.3, A.6.7 | IT Manager / HR | Lead Auditor | Interview; sample review | Training records; awareness results; remote-working controls | Planned |  | Audit Activity | Human factor / remote access
IA-11 | 2026-08-28 | 11:00–12:00 | Corrective Actions & Follow-up | Verify previous findings and current corrective actions are addressed and effective. | Corrective Action Register; audit evidence | GRC / Compliance Lead | Lead Auditor | Follow-up; evidence review | CAR records; implementation evidence; effectiveness checks | Planned |  | Audit Activity | Recurring nonconformity
IA-12 | 2026-08-28 | 15:00–16:00 | Closing Meeting | Present audit conclusions, findings, observations and next steps. | Audit results; evidence; findings criteria | Management / Process Owners | Lead Auditor | Meeting | Attendance; findings acknowledgement; action plan | Planned |  | Closing | All findings

## Audit Objectives
Objective ID
OBJ-01 | Evaluate whether the ISMS processes are established and maintained against defined audit criteria. | Required documented information exists, responsibilities are defined, and processes operate as planned.
OBJ-02 | Assess whether information-security risks are identified, evaluated and treated consistently. | Risk methodology is applied; significant risks have owners and treatment actions; decisions are traceable.
OBJ-03 | Assess implementation of selected Annex A controls based on risk and SoA applicability. | Applicable controls have evidence demonstrating implementation and, where appropriate, operation.
OBJ-04 | Evaluate operating effectiveness of high-priority controls. | Sampled controls operate consistently and evidence supports the conclusion.
OBJ-05 | Determine whether corrective actions are managed and effective. | Root causes, actions, evidence and effectiveness checks are documented and tracked.
OBJ-06 | Identify opportunities to improve the ISMS and reduce material information-security risk. | Improvement opportunities are supported by objective evidence and linked to risk or process performance.

## Sampling Plan
Sample ID
S-01 | User accounts | 10 accounts including 3 privileged users and 2 recent joiners/movers/leavers | Risk-based focus on elevated access and lifecycle changes. | Sample list; approvals; access review; MFA status
S-02 | Access reviews | Latest quarterly review plus selected prior review | Test current implementation and recurring operation. | Completed review; approvals; remediation records
S-03 | Vulnerability tickets | 5 remediation records across critical/high findings | Test prioritization, SLA compliance and verification. | Scan result; ticket; remediation proof; retest
S-04 | Backups | 3 critical workloads plus latest restore test | Focus on recoverability rather than backup-job success alone. | Backup status; restore evidence; recovery result
S-05 | Production changes | 5 recent significant changes | Test authorization, testing, approval and traceability. | Change tickets; approvals; test results; deployment logs
S-06 | Security alerts | 10 alerts across severity levels | Assess monitoring, investigation and escalation. | Alert records; analyst actions; escalation evidence
S-07 | Repository access | 3 critical repositories | Focus on sensitive source code and privileged permissions. | Repository access; branch protection; approvals
S-08 | Training records | 10 personnel across departments | Test awareness completion and coverage. | Training completion; simulation results
S-09 | Corrective actions | All open major/minor actions in register | Verify accountability and progress of significant findings. | CAR record; evidence; effectiveness check

## Auditor Checklist
Check ID | Audit Question | Evidence / Record | Result | Finding ID | Auditor Notes
CHK-01 | Is the ISMS scope documented and current? |  | Not Tested
CHK-02 | Is the risk assessment methodology defined and consistently applied? |  | Not Tested
CHK-03 | Are significant risks assigned owners and treatment actions? |  | Not Tested
CHK-04 | Does the SoA justify applicable controls and their status? |  | Not Tested
CHK-05 | Are access rights approved, reviewed and removed when no longer needed? |  | Not Tested
CHK-06 | Is MFA implemented for applicable accounts, including privileged accounts? |  | Not Tested
CHK-07 | Are vulnerabilities identified, prioritized and remediated? |  | Not Tested
CHK-08 | Are secure configurations defined, monitored and exceptions controlled? |  | Not Tested
CHK-09 | Are backups protected and restoration periodically tested? |  | Not Tested
CHK-10 | Are security logs retained and reviewed? |  | Not Tested
CHK-11 | Are security alerts monitored, investigated and escalated? |  | Not Tested
CHK-12 | Are secure coding and security testing practices applied? |  | Not Tested
CHK-13 | Are development, test and production environments appropriately separated? |  | Not Tested
CHK-14 | Are production changes authorized, tested and traceable? |  | Not Tested
CHK-15 | Are corrective actions subject to effectiveness verification? |  | Not Tested

## Audit Guidance
Internal Audit Plan Guidance
Purpose | The plan defines what will be audited, against which criteria, when, by whom, and using which audit methods.
Audit criteria | Criteria may include ISO/IEC 27001 requirements, approved ISMS policies, the Statement of Applicability, risk-treatment requirements, and applicable legal or contractual obligations.
Risk-based planning | Audit time and sampling should be weighted toward significant risks, critical processes, previous findings, major changes and controls with higher potential impact.
Audit methods | Use interviews, observation, document review, sampling, system/configuration review and walkthroughs as appropriate.
Objective evidence | Record sufficient evidence to support the audit conclusion. Avoid relying solely on verbal statements.
Independence | Auditors should be sufficiently independent of the activity being audited and should avoid auditing their own work where practical.
Findings | Findings should be based on objective evidence and explicit audit criteria. Do not classify a condition as a nonconformity without a clear criterion and evidence gap.
Sampling | Samples in this portfolio are illustrative. A real audit should determine sample size and selection using the audit scope, population, risk and audit objectives.
Portfolio note | This is a simulated internal audit plan for a GRC portfolio and is not an actual audit programme or certification audit.