## Finding Register
ABC Cloud Technologies Ltd. — Audit Finding Register
Portfolio working paper ¦ ISO/IEC 27001:2022 ¦ Internal Audit IA-2026-001 ¦ Version 1.0
Audit ID | IA-2026-001 | Audit Report | Internal_Audit_Report.pdf | Finding Owner | GRC / Compliance Lead | Review Cycle | Monthly
Purpose | Central register for audit observations and nonconformities, with traceability from audit criteria and evidence through corrective action and effectiveness verification.
Finding ID | Audit Check ID | Classification | ISO/IEC 27001 Criterion | Annex A / Control | Process / Area | Requirement / Expected Condition | Actual Condition / Gap | Objective Evidence | Risk / Impact | Risk Rating | Finding Statement | Root Cause | Corrective Action | Action Owner | Target Date | Status | Implementation Evidence | Effectiveness Check | Closure Decision | Closure Date
F-001 | CHK-015 | Major Nonconformity | Clause 8.1; applicable access-control requirements | A.5.15, A.5.17, A.8.2 | Privileged Access / MFA | Privileged access should be authorized, restricted, authenticated appropriately, reviewed and controlled. | Evidence does not consistently demonstrate complete privileged-account inventory, MFA coverage, periodic recertification and documented exception handling. | Privileged-access register; sampled account records; MFA evidence; access-review records. | Compromised or excessive privileged access could enable unauthorized system changes, data exposure or broad compromise. | High | Privileged-access governance and authentication evidence are not consistently sufficient to demonstrate effective control across all elevated accounts. | Lifecycle ownership and periodic privileged-access recertification are not consistently formalized. | Create a complete privileged-account inventory; enforce applicable MFA; formalize approval and quarterly recertification; document exceptions; perform effectiveness review. | IT / Security Lead | 2026-09-23 | Open |  | Pending | Open
F-002 | CHK-021 | Minor Nonconformity | Clause 8.1; applicable availability/recovery requirements | A.8.13, A.5.30 | Backup & Recovery | Critical information and systems should have protected backups and restoration capability that is periodically tested. | Backup evidence exists, but restoration testing is not consistently demonstrated for all critical workloads. | Backup logs; retention settings; sampled restore-test records. | Failure to restore critical data after ransomware, corruption or outage could cause material service disruption or data loss. | High | Backup evidence exists, but restoration testing and documented recovery verification are not consistently demonstrated for all critical workloads. | Restore-test coverage is not fully mapped to the critical-workload inventory. | Define critical-workload restore-test coverage, execute tests, retain results and track failed tests to corrective action. | IT Manager | 2026-09-23 | Open |  | Pending | Open
F-003 | CHK-023 | Minor Nonconformity | Clause 8.1; monitoring requirements | A.8.15, A.8.16 | Logging & Monitoring | Relevant security events should be logged, monitored and reviewed using defined responsibilities and escalation criteria. | Logging and monitoring requirements exist, but evidence of periodic review and consistent alert handling is incomplete. | SIEM/log records; alert tickets; review evidence; escalation records. | Delayed detection or inconsistent alert handling could increase the impact of security incidents. | High | Logging and monitoring requirements are established, but evidence of periodic review and consistent alert handling requires improvement. | Monitoring review responsibilities and evidence-retention requirements are not consistently documented. | Define review frequency, alert ownership, escalation criteria and evidence retention; perform periodic QA review. | Security Lead | 2026-10-08 | Open |  | Pending | Open
F-004 | CHK-026 | Minor Nonconformity | Clause 8.1; secure development requirements | A.8.28 | Secure Development | Secure coding practices and security testing should be integrated into development and supported by retained evidence. | Secure coding and security-testing evidence is not consistently retained across sampled releases. | Code-review records; security-test results; release records. | Unverified security testing may allow exploitable defects to reach production. | Medium | Secure coding and security-testing evidence is not consistently retained across sampled releases. | Release evidence requirements are not standardized across development teams. | Define mandatory secure-development evidence for releases and implement a release checklist with exception approval. | Engineering Lead | 2026-10-23 | Open |  | Pending | Open

## Traceability
Finding ID | Audit Check | Requirement / Criterion | Evidence Source | Risk Register Link | Risk Treatment Link | Corrective Action Link | Audit Report Section | Closure Evidence
F-001 | CHK-015 | Clause 8.1; A.5.15/A.5.17/A.8.2 | Privileged access + MFA evidence | R-001 / R-005 / R-011 | RTP-001 | CAR-001 | Section 7 | To be collected
F-002 | CHK-021 | Clause 8.1; A.8.13/A.5.30 | Backup and restore evidence | R-007 | RTP-007 | CAR-002 | Section 8 | To be collected
F-003 | CHK-023 | Clause 8.1; A.8.15/A.8.16 | Logging and monitoring evidence | R-008 | RTP-008 | CAR-003 | Section 8 | To be collected
F-004 | CHK-026 | Clause 8.1; A.8.28 | Secure-development evidence | R-004 | RTP-004 | CAR-004 | Section 8 | To be collected

## Follow-up Log
Follow-up ID | Finding ID | Verification Date | Action Implemented? | Evidence Reviewed | Effectiveness Test | Result | Verifier | Closure Recommendation | Comments
FU-001 | F-001 |  | Pending |  |  | Pending
FU-002 | F-002 |  | Pending |  |  | Pending
FU-003 | F-003 |  | Pending |  |  | Pending
FU-004 | F-004 |  | Pending |  |  | Pending

## Summary Dashboard
Audit Finding Summary
Metric | Value | Interpretation | Action
Total findings | 4 | All findings require controlled follow-up. | Track monthly
Major nonconformities | 1 | Highest priority finding. | Immediate corrective action
Minor nonconformities | 3 | Limited control gaps requiring correction. | Correct and verify
Observations | 0 | No observation-only finding recorded in this simulated report. | Monitor
Open findings | 4 | No finding is closed yet. | Do not close without verification
Pending effectiveness checks | 4 | Effectiveness must be demonstrated after implementation. | Schedule follow-up

## Instructions
How to Use the Audit Finding Register
1. Record finding | Every observation/nonconformity identified during the audit receives a unique Finding ID.
2. Link the evidence | Enter the exact objective evidence used to support the finding. Avoid unsupported statements.
3. State the criterion | Identify the ISO/IEC 27001 requirement, Annex A control, policy or other audit criterion.
4. Describe the gap | Separate the expected condition from the actual condition so the nonconformity is clear.
5. Assess risk | Explain the security/business impact and use the risk rating consistently with the organization's risk methodology.
6. Corrective action | Actions should address the cause, not merely the symptom. Assign an owner and target date.
7. Verify effectiveness | Implementation alone does not close a finding. The auditor should verify evidence and test whether the control now works as intended.
8. Closure | Close only when implementation and effectiveness are demonstrated and the closure decision is documented.
Lead Auditor principle | Findings must be based on objective evidence and defined audit criteria. Avoid grading based on opinion or assumptions.
Portfolio note | All organization details, findings, dates and evidence are simulated for portfolio purposes.