## Effectiveness Review
ABC Cloud Technologies Ltd. — Risk Treatment Effectiveness Review
Portfolio working paper ¦ ISO/IEC 27001:2022 ¦ Version 1.0 ¦ August 2026
Review ID | RTER-2026-001 | Review Date | 2026-08-31 | Reviewer | GRC / Compliance Lead | Frequency | Quarterly
Purpose | Evaluate whether implemented risk treatments are operating as intended and whether residual risk is reduced to an acceptable level. | [5 empty] | 2026-11-30
Review ID | Risk ID | Risk Description | Risk Owner | Treatment Ref | Treatment / Control | Pre-Treatment Likelihood | Pre-Treatment Impact | Pre-Treatment Score | Implemented Treatment | Evidence Reviewed | Post-Treatment Likelihood | Post-Treatment Impact | Residual Score | Acceptance Threshold | Within Threshold? | Effectiveness Result | Control Performance Evidence | Open Issue / Gap | Action Required | Next Review
RTER-001 | R-001 | Unauthorized access to customer systems/data | IT / Security Lead | RTP-001 | Enforce MFA, quarterly access reviews, least privilege and privileged-account monitoring. | 4 | 5 |  | Implemented for in-scope accounts; privileged account review established. | MFA report; access review record; privileged-access register; sample test results. | 2 | 5 |  | 10 | Yes | Effective | Sampled privileged accounts had MFA; access review completed; exceptions documented. | Complete remaining legacy/service-account coverage. | Extend MFA and review coverage to remaining service accounts; verify next cycle. | 2026-11-30
RTER-002 | R-002 | Source-code exposure or unauthorized repository access | Engineering Lead | RTP-002 | Repository role-based access, branch protection, code review and security testing. | 4 | 4 |  | Repository permissions restricted and branch protection enabled. | Repository access export; branch-protection settings; code-review records. | 2 | 4 |  | 8 | Yes | Effective | Critical repositories sampled; privileged access limited; protected branches enabled. | Security-test evidence is not retained consistently for every release. | Standardize release security evidence and verify in next release sample. | 2026-11-30
RTER-003 | R-003 | Cloud misconfiguration or insecure infrastructure | IT Manager | RTP-003 | Secure cloud baseline, configuration monitoring and exception management. | 5 | 5 |  | Baseline implemented and configuration monitoring enabled for critical services. | Cloud configuration report; baseline; exception register; remediation tickets. | 3 | 5 |  | 10 | Yes | Partially Effective | Critical services meet baseline; some configuration exceptions remain open. | Open configuration exceptions exceed internal remediation target. | Close overdue exceptions and retest configuration compliance. | 2026-10-31
RTER-004 | R-004 | Unpatched vulnerability exploited | Engineering Lead | RTP-004 | Continuous vulnerability scanning, risk-based remediation and verification. | 4 | 5 |  | Scanning and remediation workflow operational. | Vulnerability scan; remediation tickets; retest evidence. | 2 | 5 |  | 10 | Yes | Effective | Critical/high vulnerabilities sampled had owners and remediation evidence. | None material identified in current sample. | Continue monthly scanning and SLA monitoring. | 2026-11-30
RTER-005 | R-005 | Excessive or stale user privileges | IT Manager | RTP-005 | Joiner-mover-leaver process, access approvals and periodic recertification. | 4 | 4 |  | JML process and quarterly access review implemented. | JML tickets; access matrix; quarterly review evidence. | 2 | 4 |  | 8 | Yes | Effective | Recent lifecycle events sampled were processed; access review completed. | Legacy accounts require cleanup. | Complete legacy-account remediation and verify next review. | 2026-11-30
RTER-006 | R-006 | Malware or endpoint compromise | IT Manager | RTP-006 | Endpoint protection, centralized alerting and patching. | 4 | 5 |  | Endpoint protection deployed to in-scope endpoints. | EDR dashboard; endpoint compliance report; alert records. | 2 | 5 |  | 10 | Yes | Effective | Sampled endpoints reported active protection and current status. | Monitor exceptions and unsupported endpoints. | Remediate unsupported endpoints and track exceptions. | 2026-10-31
RTER-007 | R-007 | Data loss due to backup/recovery failure | IT Manager | RTP-007 | Protected backups, retention controls and periodic restoration testing. | 4 | 5 |  | Backups operational; restoration testing partially completed. | Backup logs; retention configuration; restore-test records. | 2 | 5 |  | 10 | Yes | Partially Effective | Backup jobs successful for sampled workloads; restore evidence incomplete for all critical workloads. | Critical-workload restore testing is not yet complete. | Complete restore testing and document recovery results. | 2026-09-23
RTER-008 | R-008 | Security event not detected or escalated | Security Lead | RTP-008 | Centralized logging, SIEM monitoring, alert triage and escalation. | 4 | 5 |  | Centralized monitoring implemented; alert review process established. | SIEM records; alert tickets; review logs; escalation records. | 2 | 5 |  | 10 | Yes | Partially Effective | Monitoring is active; evidence of consistent periodic review is incomplete. | Review evidence and escalation records require stronger consistency. | Formalize review evidence and conduct QA sampling. | 2026-10-08
RTER-009 | R-009 | Remote access exposes corporate information | IT Manager | RTP-009 | Remote-working policy, MFA, endpoint compliance and secure remote access. | 4 | 4 |  | Remote access protected by MFA and endpoint requirements. | Remote access policy; MFA report; endpoint compliance. | 2 | 4 |  | 8 | Yes | Effective | Sampled remote users met MFA and endpoint requirements. | None material identified. | Continue periodic compliance monitoring. | 2026-11-30
RTER-010 | R-010 | Unauthorized production change | Engineering Lead | RTP-010 | Formal change approval, testing, separation of environments and deployment traceability. | 3 | 5 |  | Change workflow and approval controls implemented. | Change tickets; approvals; test evidence; deployment logs. | 2 | 5 |  | 10 | Yes | Effective | Sampled production changes had approvals and traceability. | None material identified. | Continue monthly change sampling. | 2026-11-30
RTER-011 | R-011 | Incident response delayed or ineffective | Security Lead | RTP-011 | Incident response plan, roles, escalation and exercises. | 3 | 5 |  | Incident response process established; exercise conducted. | Incident response plan; exercise record; incident tickets. | 2 | 5 |  | 10 | Yes | Effective | Roles and escalation paths documented; exercise actions tracked. | Continue testing response readiness. | Perform next tabletop exercise and close open actions. | 2026-12-15

## Risk Scoring
Likelihood | Meaning |  | Impact | Meaning | Score | Interpretation
1 | Rare
2 | Unlikely
3 | Possible
4 | Likely
5 | Almost Certain
|  | 1 | Insignificant
|  | 2 | Minor
|  | 3 | Moderate
|  | 4 | Major
|  | 5 | Severe
[5 empty] | 1 | Very Low
[5 empty] | 2 | Very Low
[5 empty] | 3 | Low
[5 empty] | 4 | Low
[5 empty] | 5 | Medium
[5 empty] | 6 | Medium
[5 empty] | 7 | Medium
[5 empty] | 8 | High
[5 empty] | 9 | High
[5 empty] | 10 | High
[5 empty] | 12 | High
[5 empty] | 15 | Critical
[5 empty] | 16 | Critical
[5 empty] | 20 | Critical
[5 empty] | 25 | Critical

## Review Summary
Risk Treatment Effectiveness Review — Management Summary
Total risks reviewed | 11
Effective | 8
Partially Effective | 3
Not Effective | 0
High residual score (>=8) | 11
Key conclusion | Most treatments demonstrate effective or partially effective implementation; high-priority follow-up is required for cloud exceptions, backup restoration testing and monitoring evidence.
Management actions | Prioritize open treatment gaps, assign owners, track target dates and re-evaluate residual risk after corrective actions.

## Instructions
How to Use This Review
Purpose | Determine whether risk treatments are implemented, operating as intended and reducing residual risk to an acceptable level.
Step 1 — Establish baseline | Record the pre-treatment likelihood and impact using the organization's approved risk methodology.
Step 2 — Verify implementation | Review objective evidence showing that the planned treatment was actually implemented.
Step 3 — Test effectiveness | Assess whether the treatment operates as intended. Use sampling, testing, metrics, incidents, audit evidence and control performance data.
Step 4 — Recalculate residual risk | Record post-treatment likelihood and impact and calculate the residual score.
Step 5 — Compare to threshold | Determine whether residual risk is within the approved risk-acceptance threshold.
Step 6 — Record gaps | If treatment is only partially effective or not effective, document the gap and required action.
Step 7 — Follow up | Assign an owner and target date, then repeat the effectiveness review after remediation.
Lead Auditor interview point | An auditor should not accept 'control implemented' as proof of effectiveness. Effectiveness requires objective evidence that the treatment achieves its intended risk-reduction outcome.
Portfolio note | All organization details, dates, scores and evidence are simulated for portfolio purposes.