## Management Review
ABC Cloud Technologies Ltd. — ISMS Management Review Meeting Pack
ISO/IEC 27001:2022 ¦ Portfolio Simulation ¦ Meeting ID: MR-2026-001 ¦ Version 1.0
Meeting Date | 2026-09-05 | Chair | Executive Sponsor | ISMS Owner | GRC / Compliance Lead | Review Period | Q3 2026
Purpose | Evaluate ISMS suitability, adequacy and effectiveness; review risks, audit results, treatment effectiveness, performance and improvement actions. |  | Executive Sponsor; GRC Lead; IT Manager; Security Lead; Engineering Lead |  | N/A — initial portfolio review |  | 2026-12-05
1. Management Review Inputs
Input |  |  | Status / Result |  | Management Discussion / Decision
Internal audit results |  |  | 4 findings: 1 major NC, 3 minor NC |  | Prioritize F-001 and verify all corrective actions.
Risk register / risk profile |  |  | 11 key risks reviewed; high-priority residual risks remain |  | Review treatment gaps and risk acceptance.
Risk treatment effectiveness |  |  | 8 effective, 3 partially effective |  | Require follow-up on cloud, backup and monitoring.
Corrective actions |  |  | 4 audit findings open |  | Assign owners, deadlines and effectiveness verification.
ISMS objectives / KPIs |  |  | Control evidence exists but monitoring maturity varies |  | Standardize KPI collection and management reporting.
Legal / regulatory / contractual changes |  |  | No material change recorded in simulation |  | Confirm applicable requirements at next review.
Security incidents / events |  |  | No major incident recorded in simulation |  | Continue monitoring and exercise response readiness.
Resources / competence |  |  | GRC, IT, Security and Engineering ownership defined |  | Assess training, tooling and staffing needs.
Opportunities for improvement |  |  | Evidence consistency, privileged access and testing maturity |  | Approve improvement actions and track to closure.
2. Required Management Review Outputs
Decision / Output | Decision Required | Proposed Decision | Owner | Due Date | Status | Evidence / Reference | Management Notes
ISMS suitability | Is the ISMS aligned to business/security needs? | Yes, with targeted improvements. | Executive Sponsor | 2026-09-05 | Approved | ISMS scope; risk profile | Maintain current scope; improve evidence maturity.
ISMS adequacy | Are resources, processes and controls sufficient? | Partially — additional control assurance needed. | Executive Sponsor / IT | 2026-09-30 | Open | Audit findings; KPI summary | Review privileged access, backup and monitoring resources.
ISMS effectiveness | Are controls reducing information-security risk? | Generally effective; 3 treatments require follow-up. | GRC Lead | 2026-10-31 | Open | Risk Treatment Effectiveness Review | Re-test partially effective treatments.
Corrective actions | Approve action priorities and deadlines. | Approve all 4 findings and assigned owners. | GRC Lead | 2026-09-10 | Approved | Audit Finding Register | Track monthly until closure.
Risk acceptance | Accept remaining residual risk? | No new acceptance for unresolved high-priority gaps. | Executive Sponsor | 2026-09-10 | Approved | Risk Register | Escalate if treatment deadlines are missed.
Improvement actions | Approve continual-improvement actions. | Approve 5 improvement actions. | GRC Lead | 2026-09-15 | Approved | Improvement Register | Monitor through next management review.

## ISMS KPIs
KPI ID | KPI | Target | Current / Simulated Result | Status | Trend | Owner | Management Action
KPI-01 | Critical vulnerabilities remediated within SLA | >=95% | 92% | Needs Improvement | ↔ | IT Manager | Review overdue critical findings.
KPI-02 | Privileged accounts with MFA | 100% | 96% | Needs Improvement | ↑ | Security Lead | Close remaining exceptions.
KPI-03 | Quarterly access reviews completed | 100% | 100% | Achieved | → | IT Manager | Maintain.
KPI-04 | Successful backup jobs | >=98% | 99% | Achieved | → | IT Manager | Maintain and test restoration.
KPI-05 | Critical workload restore tests completed | 100% | 75% | Needs Improvement | ↑ | IT Manager | Complete remaining restore tests.
KPI-06 | Security alerts reviewed within defined SLA | >=95% | 91% | Needs Improvement | ↑ | Security Lead | Strengthen review evidence and escalation.
KPI-07 | Production changes with approved record | 100% | 100% | Achieved | → | Engineering Lead | Maintain.
KPI-08 | Mandatory security training completion | 100% | 97% | Needs Improvement | ↑ | GRC Lead | Close outstanding training.
KPI-09 | Open major audit findings | 0 | 1 | Needs Improvement | ↓ | GRC Lead | Prioritize F-001.
KPI-10 | Corrective actions overdue | 0 | 0 | Achieved | → | GRC Lead | Maintain monthly tracking.

## Risk Summary
Risk ID | Risk Description | Pre-Treatment Score | Residual Score | Effectiveness | Risk Owner | Open Gap | Management Decision
R-001 | Unauthorized access to customer systems/data | 20 | 10 | Effective | IT / Security Lead | Legacy/service-account coverage | Continue monitoring; close exceptions.
R-002 | Source-code exposure or unauthorized repository access | 16 | 8 | Effective | Engineering Lead | Release security evidence consistency | Standardize release evidence.
R-003 | Cloud misconfiguration or insecure infrastructure | 25 | 15 | Partially Effective | IT Manager | Open configuration exceptions | Escalate overdue exceptions.
R-004 | Unpatched vulnerability exploited | 20 | 10 | Effective | Engineering Lead | None material | Maintain SLA monitoring.
R-005 | Excessive or stale user privileges | 16 | 8 | Effective | IT Manager | Legacy accounts | Complete cleanup.
R-006 | Malware or endpoint compromise | 20 | 10 | Effective | IT Manager | Unsupported endpoint exceptions | Remediate exceptions.
R-007 | Data loss due to backup/recovery failure | 20 | 10 | Partially Effective | IT Manager | Restore testing incomplete | Complete testing.
R-008 | Security event not detected or escalated | 20 | 10 | Partially Effective | Security Lead | Review evidence consistency | Formalize QA sampling.
R-009 | Remote access exposes corporate information | 16 | 8 | Effective | IT Manager | None material | Continue monitoring.
R-010 | Unauthorized production change | 15 | 10 | Effective | Engineering Lead | None material | Continue sampling.
R-011 | Incident response delayed or ineffective | 15 | 10 | Effective | Security Lead | Exercise follow-up | Continue testing.

## Audit Findings
Finding ID | Classification | Area | Summary | Owner | Target Date | Status | Management Decision
F-001 | Major Nonconformity | Privileged Access / MFA | Privileged-access governance and MFA evidence is not consistently sufficient. | IT / Security Lead | 2026-09-23 | Open | Priority 1 — immediate corrective action and effectiveness test.
F-002 | Minor Nonconformity | Backup & Recovery | Restore testing is incomplete for all critical workloads. | IT Manager | 2026-09-23 | Open | Priority 2 — complete restoration testing.
F-003 | Minor Nonconformity | Logging & Monitoring | Evidence of periodic review and alert handling is inconsistent. | Security Lead | 2026-10-08 | Open | Priority 3 — strengthen monitoring evidence.
F-004 | Minor Nonconformity | Secure Development | Security testing evidence is not consistently retained across releases. | Engineering Lead | 2026-10-23 | Open | Priority 4 — standardize release evidence.

## Management Action Plan
Action ID | Source | Action | Owner | Priority | Target Date | Success Measure | Status | Evidence | Review Date
MR-A01 | F-001 | Complete privileged-account inventory, MFA coverage and quarterly recertification. | IT / Security Lead | Critical | 2026-09-23 | 100% in-scope privileged accounts reviewed and MFA compliant. | Open |  | 2026-10-01
MR-A02 | F-002 | Complete restore testing for critical workloads. | IT Manager | High | 2026-09-23 | 100% critical workloads have documented restore-test evidence. | Open |  | 2026-10-01
MR-A03 | F-003 | Formalize logging review, alert ownership and evidence retention. | Security Lead | High | 2026-10-08 | >=95% sampled alerts have documented review/escalation evidence. | Open |  | 2026-10-15
MR-A04 | F-004 | Standardize secure-development evidence in release checklist. | Engineering Lead | Medium | 2026-10-23 | 100% sampled releases retain required security evidence. | Open |  | 2026-11-01
MR-A05 | MR-IMPR-01 | Improve ISMS KPI reporting and evidence consistency. | GRC Lead | Medium | 2026-10-31 | Monthly KPI pack consistently populated and reviewed. | Open |  | 2026-11-05

## Minutes & Decisions
Agenda Item | Discussion / Evidence | Decision | Decision Owner | Due Date | Action ID | Status
Audit results | Internal audit identified 1 major and 3 minor nonconformities. | Approve corrective actions and priority order. | Executive Sponsor | 2026-09-10 | MR-A01 to MR-A04 | Open
Risk treatment effectiveness | 8 effective; 3 partially effective treatments. | Require follow-up on R-003, R-007 and R-008. | GRC Lead | 2026-10-31 | MR-A01 to MR-A03 | Open
ISMS performance | Several KPIs below target. | Improve monitoring, restoration testing and MFA coverage. | Relevant Owners | 2026-10-31 | MR-A01 to MR-A05 | Open
Resources | Current ownership defined; additional assurance effort required. | Review tooling/training needs in next review. | Executive Sponsor | 2026-11-15 | MR-A05 | Open
Continual improvement | Evidence maturity and control assurance need improvement. | Approve improvement programme and monthly tracking. | GRC Lead | 2026-09-15 | MR-A05 | Open

## Instructions
How to Use the Management Review Pack
Purpose | Provide top management with a structured view of ISMS performance, risks, audit results, treatment effectiveness, corrective actions and improvement needs.
ISO 27001 focus | Management review should evaluate whether the ISMS remains suitable, adequate and effective, and whether decisions/actions are needed for improvement or change.
Before the meeting | Update KPIs, risk status, audit findings, treatment effectiveness, incidents, legal/regulatory changes, resource needs and previous action status.
During the meeting | Discuss evidence, record decisions, assign owners and due dates, and document whether risks are accepted, treated or escalated.
After the meeting | Track every decision/action to completion and retain meeting records as documented information.
Lead Auditor evidence | Minutes, attendance, inputs reviewed, decisions, action owners, due dates and follow-up evidence should be retained.
Portfolio note | All company data, dates, metrics, risks and findings are simulated for a cybersecurity GRC portfolio project.